## Sheet1
Project | Module | Functionality | URL | Issue Type | Query | Date of login | Issue Status
Retail Shopping | User | User Login | http://retailm1.upskills.in/account/login | requirement | If a returning cutomer forgets password, there | 2021-09-01 | open
should be an option to to change password.
Retail Shopping | User | User Registration | http://retailm1.upskills.in/account/register | requirement | All state names should be there in State | 2021-09-01 | open
dropdown option.
Retail Shopping | User | User Registration | http://retailm1.upskills.in/account/register | requirement | Length of maximum characters in telephone | 2021-09-01 | open
should be only 12 not 32
Retail Shopping | User | User Registration | http://retailm1.upskills.in/account/register | requirement | By default no radio button should be selected | 2021-09-01 | open
for newsletter option.
Retail Shopping | User | User Registration | http://retailm1.upskills.in/account/register | requirement | Verified email should only be allowed to enter. | 2021-09-01 | open
Retail Shopping | User | User Registration | http://retailm1.upskills.in/account/register | requirement | Email address without @ symbol should | 2021-09-01 | open
not be allowed.