## Sheet1
Project: Retail Shopping Project
Organised By: Nandita Kumari
Date: 06-09-21
Test Cases and Execution Status Tracking
Creation of test Cases
Sl No. | Module | No of test cases | Date | Estimated Effort (in mins) | Actual Effort(in mins) | Reason for variance if any
1 | User Login | 6 | 2021-09-03 | 60 | 90 | N/A
2 | User Registration | 26 | 2021-09-03 | 210 | 240 | N/A
3 | Admin Notification | 8 | 2021-09-04 | 90 | 120 | N/A
4 | Admin Store | 2 | 2021-09-04 | 30 | 30 | N/A
Total No of Test Cases: 354

## Sheet2
Execution of Test Cases
|  |  | Defects |  |  | No. of Defects
Sl. No. | Module | No of Test cases | H | M | L